# Draft CRO SoW

Project: tnaas-HDAC6-v2-benchmark

Targets: HDAC6

Molecules: 1

## Line Items

Assay setup and validation

Primary screening (per target)

Counterscreens and orthogonal assays

ADMET panel (hERG/CYP/solubility/permeability)

## Timeline (weeks)

Week 1–2: Setup & validation

Week 3–4: Primary runs

Week 5: Counterscreens & ADMET